## Sheet1
Task | Task 2 | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Review Course Syllabus & Project Requirements | P0 | Azeneth Castañeda | Completed | 2026-08-28 | 2026-09-03 | Course Kickoff Checkpoint |  | Class 1 baseline tracking established.
Perform Comparitive Research (SpotHero, ParkMobile, Google Maps) | P1 | Azeneth Castañeda | Completed | 2026-09-04 | 2026-09-09 | Market Research Finalization |  | Identified navigation & real-time tool gaps.
Draft Initial Vision & Scope Document | P0 | Azeneth Castañeda | Completed | 2026-09-10 | 2026-09-16 | Scope Definition Lock |  | Mapped out target business needs.
Formulate 15 System Use Cases & Functional MatriX | P0 | Azeneth Castañeda | Completed | 2026-09-11 | 2026-09-17 | Homework 2 Submission |  | Due Sept. 17th by 11:59 PM
Build Hierarchical Work Breakdown Struture (WBS) Blocks | P1 | Azeneth Castañeda | Completed | 2026-09-18 | 2026-09-24 | Homework 3 Submission |  | Due Sept. 24th. Decomposing system components
Apply Software Workload Estimations (Story Points & COCOMO Models) | P1 | Azeneth Castañeda | Completed | 2026-09-25 | 2026-10-01 | Homework 4 Submission |  | Due Oct. 1st. Modeling framework rules.
Design UI/UX Wireframe Dashboard Views (Web & Mobile Formats) | P2 | Azeneth Castañeda | Completed | 2026-10-02 | 2026-10-08 | Homework 5 Submission |  | Due Oct. 8. User experience blueprint mapping
Navigation Map Overlay & Payment Processing Gateway APIs | P1 | Azeneth Castañeda | Completed | 2026-10-09 | 2026-10-15 | Homework 6 Submission |  | Due Oct 15th. Third-party dependency validation.
Milestone: Complete Midterm Exam Evaluation Review | P0 | Azeneth Castañeda | In progress | 2026-10-16 | 2026-10-16 | Classroom Evaluation Milestone |  | Midterm evaluation milestone on Oct 16th.
Develop Profile Authorization & Secure Sign In Portals (FRI) | P1 | Azeneth Castañeda | Not started | 2026-10-17 | 2026-10-29 | Homework 7 Submission |  | Due Oct 29th. Profile validation controls.
Integrate Real-Time Map Displays & Spot Tracking Modules | P0 | Azeneth Castañeda | Not started | 2026-10-30 | 2026-11-05 | Homework 8 Submission |  | Due Nov 5th. Core operational logic component.
Construct Transaction Engines & Automated Recipt Generators | P1 | Azeneth Castañeda | Not started | 2026-10-06 | 2026-11-12 | Homework 9 Submission |  | Due Nov 12th. Billing engine processing system
Build Analytical Administrative Portals for Lot Operators | P2 | Azeneth Castañeda | Not started | 2026-11-13 | 2026-11-19 | Operator Panel Feature Check |  | Operational reporting data visuals logic.
Milestone: Complete Advanced Project Architecture Review | P0 | Azeneth Castañeda | Not started | 2026-11-20 | 2026-11-20 | Classroom Evaluation Milestone |  | Advanced system architecture evaluation review.
Run Peak Hour Concurrent High-load Verification Routines | P1 | Azeneth Castañeda | Not started | 2026-11-21 | 2026-11-26 | System Stress Metrics Locked |  | Validating system scale stability parameters
Conduct User Acceptance Testing (UAT) & Fix Active System Bugs | P1 | Azeneth Castañeda | Not started | 2026-11-28 | 2026-12-03 | Golden System Master Complete |  | Resoultion of high-priority software performance bugs.
Milestone: Final Production Deployment & Code Delivery Release | P0 | Azeneth Castañeda | Not started | 2026-12-04 | 2026-12-04 | Semester Project Deadline Target |  | Due Dec 4th by 11:59 PM. Final evaluation delivery.